## Feature Comparison
Video Feature | Current Implementation | Needed Change
Step-by-step onboarding flow (email → plan → Stripe → content → arena-ready) | Separate endpoints exist, no orchestrator | Create consolidated onboarding status endpoint
Email verification (Verify now / later) | Already implemented via UserModel.activated_at | Expose pending_verification flag
Plan selection and activation | Implemented via DefaultPlan and FighterPlan | Reuse existing logic
Stripe Connect integration | Implemented in PaymentService | Reuse existing logic
Minimum content upload (photo/video) | No minimum content validation | Add content requirement check
Arena Ready checklist | No endpoint returning readiness info | Create arena-ready logic
Tipping feature | No tipping flag or persistence | Add tipping_enabled field and API
Retry Stripe onboarding | getRefreshUrl exists but not exposed | Expose retry link in onboarding response
Go Live restriction | No centralized readiness verification | Add ready flag in onboarding status
UI checklist output | No aggregated checklist endpoint | Return full checklist structure in API

## Technical Scope
Area | Technical Description | Change Type
Onboarding Orchestrator | Create endpoint /onboarding/status returning readiness and checklist | New endpoint
Arena Ready Status | Combine all readiness checks (email, plan, stripe, tipping, content) | New logic
Tipping Feature Flag | Add tipping_enabled field with GET/PATCH endpoints | New field + small API
Minimum Content Check | Ensure fighter has avatar + 1 active content | New validation
Email Verification Exposure | Expose pending_verification in profile response | Small adjustment
Stripe Retry Link | Include getRefreshUrl in onboarding status response | Reuse existing logic
Ready-to-Go Flag | Add arena_ready flag to unlock publishing | Minor adjustment
Checklist Logging | Store timestamps for step completions (optional) | Optional addition
Tests and Swagger | Document and test all new endpoints | Documentation update

## Time Estimates
Task # | Description | Hours
1 | Reuse and adapt endpoints for plans and payments. Include tipping and Stripe readiness. | 16
2 | Create consolidated endpoint returning arena-ready status and next steps. | 8
3 | Refactor update profile endpoint to include tipping and terms acceptance. | 8
4 | Refactor view profile endpoint to expose readiness flags and hide incomplete profiles. | 8
5 | Add minimum content verification in ContentService for onboarding validation. | 6
6 | Fix defects, add integration tests and Swagger documentation. | 10
7 | Meetings and sync with frontend team for flow adjustments. | 20
8 | Buffer | 80